## Backend
# | Task | Depends On | Tools / Stack | Status | 💬 Why This Matters (Plain English)
📦 PHASE 1 — Environment & Infrastructure Setup
1 | Phase 1 | — | Spotify Dev Portal, Google Cloud Console | ✅ Done | APIs are official data taps that give you legal access to streaming stats, search trends and weather. Apply early — some approvals take 2–3 days. Without approved keys, your entire data pipeline is dead on arrival.
2 | Phase 1 | Task 1 | PostgreSQL, pgAdmin / Supabase | ✅ Done | Think of this as building your filing cabinet before collecting documents. You need organised shelves for artist data, city data and concert records. Everything your model calculates gets stored and retrieved from here.
3 | Phase 1 | Task 1 | Python, FastAPI, Docker | ✅ Done | FastAPI is the calculation engine your n8n workflows will call. Whenever n8n collects data from Spotify and YouTube, it sends it here to crunch the maths and return a success score. Docker keeps it portable and easy to deploy anywhere.
4 | Phase 1 | Tasks 1,3 | Python-dotenv / AWS Secrets Manager | ✅ Done | Your API keys are like passwords. Storing them in a secure vault — not hard-coded in code — protects them from leaking. A single leaked Spotify key can get your entire API access banned permanently.
5 | Phase 1 | Task 3 | GitHub | ✅ Done | GitHub stores and version-controls all code. A branch strategy means developers can work on different features simultaneously without breaking each other's work — like Google Docs with tracked changes, but for code.
6 | Phase 1 | Tasks 2,3 | Notion / Google Sheets | ✅ Done | Before cooking, you list all ingredients. Here you define every data field: artist name, Spotify score, city income, ticket price, etc. This becomes the shared language your entire team works from and prevents costly miscommunication.
📡 PHASE 2 — Data Ingestion APIs
7 | Phase 2 | Tasks 1–5 | Python, Spotipy library | ✅ Done | Spotify assigns every artist a popularity score (0–100) and shows their top listening cities. This is your primary Artist Strength signal. For mainstream Bollywood artists like Arijit Singh it is reliable and updated weekly.
8 | Phase 2 | Tasks 1–5 | Python, google-api-python-client | ✅ Done | In India, YouTube dominates in Tier-2 and Tier-3 cities where Spotify penetration is low. A regional Assamese artist may have 50M YouTube views but only 200k Spotify listeners. Ignoring YouTube makes your model blind to half of India.
9 | Phase 2 | Tasks 1–5 | Python, pytrends | 🔲 Not Started | When fans search 'Arijit Singh concert Guwahati' on Google, that is buying intent. Google Trends gives a 0–100 score showing search intensity per city. High score = pent-up demand that translates directly into ticket purchases.
10 | Phase 2 | Tasks 1–5 | Python, requests | 🔲 Not Started | Monsoon rain or 42°C heat destroys outdoor concert attendance. This module checks historical weather for the proposed concert month. If it is typically rainy, the model penalises outdoor venues. Indoor venues are unaffected.
11 | Phase 2 | Tasks 1–5 | Python, PredictHQ API | 🔲 Not Started | If Badshah performs in Guwahati on March 15 and your client wants Arijit on March 20, local fans' budget is split. PredictHQ is a live event intelligence API that detects such conflicts. Without this, your model will wildly overestimate success.
12 | Phase 2 | Task 2 | Python, pandas, data.gov.in | ⚠️ Partial | The Indian government publishes free data on every city — average income, age groups, dominant language. Your model needs this to judge whether a city can afford a ₹2000 ticket. A city with ₹15k average income behaves very differently from one with ₹8k.
13 | Phase 2 | Task 8 | PostgreSQL, manual research | ✅ Done | A promoter cannot plan a concert without knowing what venues exist. Pre-loading major venues (stadiums, auditoriums) per city means users can select a real venue and your model uses the actual capacity — not a guess — in the friction calculation.
🧮 PHASE 3 — Mathematical Engine
14 | Phase 3 | Phase 2 complete | Python, numpy | ✅ Done | Your inputs are in completely different units — Spotify listeners (millions), income (rupees), ticket price (hundreds). Normalization converts everything to a 0–1 scale before any maths runs. Without this, a city's income number would mathematically crush all other factors.
15 | Phase 3 | Phase 2 complete | Python, scipy.stats | 🔲 Not Started | Spearman correlation checks whether Spotify and YouTube agree on an artist's popularity. For Bollywood artists they mostly do. For regional artists they diverge sharply. Knowing this stops your model from double-counting popularity and inflating scores.
16 | Phase 3 | Task 15 | Python, sklearn | 🔲 Not Started | PCA squeezes correlated Spotify and YouTube data into one clean score. Instead of feeding two overlapping numbers (which causes mathematical instability), you feed one Artist Power number. Cleaner input = more reliable and trustworthy output.
17 | Phase 3 | Task 16 | Python, pandas | ⚠️ Partial | Hip-Hop/Indie skews Spotify-heavy. Bhojpuri/Folk skews YouTube-heavy. The elasticity ratio automatically adjusts which platform's data to weight more based on genre. This makes the Artist Power score intelligent about music culture — not just raw numbers.
18 | Phase 3 | Tasks 14–17 | Python, numpy | 🔲 Not Started | The Gravity Model calculates how strongly an artist pulls an audience in a city, balanced against the friction of ticket price vs. local income. Think of it like gravity: big artist + wealthy city = strong pull. Steep ticket price + poor city = massive friction that repels buyers.
19 | Phase 3 | Task 18 | Python, numpy | 🔲 Not Started | TOPSIS compares your concert scenario to two benchmarks: best possible (sold-out Mumbai stadium) and worst possible (unknown artist, Tier-3 city, monsoon). Your concert's Ri shows how close to perfect it is. Ri = 0.78 = 78% success probability. This is the number on your dashboard.
20 | Phase 3 | Task 10 | Python | 🔲 Not Started | A multiplier applied after the core score. Outdoor venue + July in Northeast India = 0.6x penalty. Indoor venue + December Saturday = 1.15x bonus. Makes the model sensitive to real-world conditions that streaming data cannot see.
21 | Phase 3 | Task 11 | Python | 🔲 Not Started | Uses PredictHQ data to calculate how much nearby competing events eat into your audience. The closer the competing event in time, the bigger the penalty. Prevents falsely optimistic scores when the local entertainment market is already saturated.
22 | Phase 3 | Tasks 12,13 | Python | ⚠️ Partial | India has 22 official languages. A Punjabi artist in Chennai faces a language gap that reduces ticket demand. This module matches artist language against the city's dominant language from Census data. A perfect match boosts the Artist Power score; a mismatch penalises it.
23 | Phase 3 | Task 19 | Python | ✅ Done | Saturdays outsell Tuesdays significantly for live events. This simple multiplier boosts scores for Friday/Saturday shows and penalises weekday shows. A small but measurable improvement to prediction accuracy with almost no development effort.
24 | Phase 3 | Tasks 19–23 | FastAPI, Python | ✅ Done | All mathematical modules wire into one clean endpoint. n8n sends {artist, city, ticket_price, venue_type, date} and receives one success score. This endpoint IS the core product. Everything else in the stack exists to support this one calculation.
🗄️ PHASE 4 — Database, Caching & Logging
25 | Phase 4 | Task 2 | Redis | ✅ Done | Spotify and YouTube APIs have daily call limits. If 50 users search Arijit Singh on the same day, you do not want to call the API 50 times. A cache stores the result for 7 days and serves it instantly — saving cost, avoiding rate-limit bans, and making the app faster.
26 | Phase 4 | Task 2 | PostgreSQL | ⚠️ Partial | Every prediction run gets logged: artist, city, all parameters, the Ri score, timestamp. This is your future gold mine. Once you have 500+ predictions validated against real outcomes, you can train a proper ML model that is exponentially more accurate than the mathematical formula.
27 | Phase 4 | Task 26 | FastAPI, PostgreSQL | ⚠️ Partial | When a promoter returns and marks 'This show sold out' or 'We hit 40% capacity', that real-world ground truth links to the original prediction. This feedback loop is the foundation of your future ML training pipeline — the point where your product starts learning from reality.
🔐 PHASE 5 — Auth, Security & Deployment
28 | Phase 5 | Phase 4 complete | FastAPI, python-jose | ✅ Done | Without authentication, anyone on the internet could call your prediction API for free, exhausting your paid Spotify/YouTube quotas in minutes. JWT tokens verify that only your own frontend and authorised n8n workflows can access the backend. Think of it as a bouncer for your API.
29 | Phase 5 | Task 28 | FastAPI-limiter, Redis | ✅ Done | Rate limiting prevents abuse. If a single user sends 1000 prediction requests per minute, they could crash your server or exhaust your API quotas. Rate limiting caps requests per user per minute, keeping the service stable for everyone else.
30 | Phase 5 | Tasks 24,28,29 | Docker, Railway / AWS | 🔲 Not Started | Deploying moves your code from laptop to a live server. n8n and your frontend need a real URL to call — they cannot talk to your laptop. The app is not real until this step is done. Choose Railway for simplicity if AWS feels overwhelming.
31 | Phase 5 | Task 2 | pg_dump / Supabase / AWS RDS | 🔲 Not Started | If your database crashes without a backup, every prediction history and user account is gone forever. Daily automated backups are cheap insurance. Set it up once and forget about it — until the day you desperately need it.
32 | Phase 5 | Phase 5 complete | FastAPI /docs | ⚠️ Partial | FastAPI auto-generates interactive documentation at /docs. This is critical for your frontend dev and n8n builder — they need to know exactly what parameters to send and what format responses come back in. Without docs, they guess and waste hours debugging.

## n8n workflows
⚙️ N8N ORCHESTRATION TASKS — Concert Success Predictor ¦ Indian Market
Workflow automation · API orchestration · Trigger logic · Error handling · Scheduling
# | Workflow / Node | Depends On | n8n Node Type | ✅ Done (Python scheduler) | 💬 Why This Matters (Plain English)
🔧 PHASE 1 — n8n Setup & Infrastructure
1 | Phase 1 | — | n8n Cloud / Docker VPS | ✅ Done (Python scheduler) | n8n is the traffic controller of your entire system — it decides when to call Spotify, YouTube, and your Python engine, and when to return results to your dashboard. Without n8n running, no data flows exist. Set this up before any workflows are built.
2 | Phase 1 | Task 1 | n8n Credentials Manager | 🔲 Not Started | n8n has a built-in secure vault for API keys. Store all keys here — never paste them raw into nodes. If you need to rotate a key, change it once and every workflow that uses it updates automatically. Security and convenience combined.
3 | Phase 1 | Tasks 1,2 | n8n Webhook Node | ✅ Done (Python scheduler) | Every time a user clicks Predict Success on the dashboard, the frontend sends a request to this Webhook. It is the reception desk — it receives artist name, city, ticket price, and date, then routes it to all the right data-fetching workers.
4 | Phase 1 | Task 3 | n8n Error Trigger, Slack Node | ✅ Done (Python scheduler) | When a Spotify API call fails at 3am, you need to know immediately — not when a user complains the next morning. This workflow monitors all other workflows and fires an alert if anything breaks. It is your automated night watchman, working 24/7.
📡 PHASE 2 — Data Fetching Workflows
5 | Phase 2 | Backend Task 7, n8n Task 2 | HTTP Request Node (Spotify API) | 🔲 Not Started | This workflow calls Spotify, gets the artist's popularity score, genre, and monthly listeners, and passes the data downstream. Triggered automatically by the Master Webhook every time a prediction is run — no human involvement needed.
6 | Phase 2 | Backend Task 8, n8n Task 2 | HTTP Request Node (YouTube API v3) | 🔲 Not Started | Queries YouTube for how many views an artist's videos got from a specific Indian state. Crucial for Tier-2 city predictions where YouTube usage dwarfs Spotify. Without this, Guwahati predictions will be significantly and systematically wrong.
7 | Phase 2 | Backend Task 9, n8n Task 2 | HTTP Request Node (FastAPI relay) | ✅ Done (Python scheduler) | Google Trends has no direct API, so n8n calls your FastAPI microservice which runs pytrends in Python and returns the result. High search volume in a city = strong buying intent. This workflow handles that relay between n8n and your Python layer.
8 | Phase 2 | Backend Task 10, n8n Task 2 | HTTP Request Node (OpenWeatherMap) | 🔲 Not Started | Fetches historical weather averages for a city and month. n8n passes this to the Python engine which applies the Weather Multiplier. A simple 2-call workflow that stops your model from optimistically recommending outdoor shows during monsoon season.
9 | Phase 2 | Backend Task 11, n8n Task 2 | HTTP Request Node (PredictHQ API) | ✅ Done (Python scheduler) | Asks PredictHQ: are there major live events in this city within 14 days of the proposed concert? The result feeds the Cannibalization calculation. Two big concerts in one small city within two weeks will hurt both shows — your model must account for this.
10 | Phase 2 | Backend Tasks 2,12, n8n Task 2 | HTTP Request Node (Internal DB) | ✅ Done (Python scheduler) | Queries your own PostgreSQL database to retrieve the city's tier, per-capita income, dominant language, and youth population. This is the City Market Capacity vector — the demand-side foundation of your entire prediction formula.
🔀 PHASE 3 — Orchestration & Calculation
11 | Phase 3 | Phase 2 complete | n8n Merge Node, Split In Batches | ✅ Done (Python scheduler) | Instead of calling Spotify then YouTube then Google Trends one after another (15+ seconds total), n8n fires all 6 workflows simultaneously. The Merge node waits for all to finish and combines results. Total prediction time drops from ~15 seconds to ~4 seconds.
12 | Phase 3 | Task 12 | n8n Code Node (JavaScript) | ✅ Done (Python scheduler) | What if Spotify returns no data for a brand-new artist? Without validation, your Python engine receives incomplete data and crashes or produces nonsense scores. This node checks every field and substitutes sensible defaults where data is missing, making the system resilient.
13 | Phase 3 | Task 13 | n8n Code Node (JavaScript) | ✅ Done (Python scheduler) | Your FastAPI endpoint expects data in a very specific format. This node is the packaging station — it takes messy outputs from 6 different APIs and assembles them into one clean JSON object that FastAPI can read without errors. Garbage in = garbage out. This prevents the garbage.
14 | Phase 3 | Tasks 14, Backend Task 24 | HTTP Request Node (FastAPI) | 🔲 Not Started | This triggers the entire mathematical engine. n8n sends the assembled data package to your FastAPI microservice and waits for the Ri score to come back. Everything built in the Backend Math Engine phase executes inside this single HTTP call.
15 | Phase 3 | Task 15 | n8n Code Node (JavaScript) | ✅ Done (Python scheduler) | FastAPI returns a raw number like 0.73. Your frontend needs more: the score, a Tier B - Profitable label, which factors helped/hurt, and the recommended venue size. This node converts a raw mathematical output into a rich, user-friendly response object.
16 | Phase 3 | Task 16 | n8n Respond to Webhook Node | ✅ Done (Python scheduler) | The last step of every prediction. After all calculations are done, this node sends the final result back to the frontend dashboard that initiated the request. Without this node, the frontend hangs forever waiting for a response that never arrives.
⏰ PHASE 4 — Scheduled & Maintenance Workflows
17 | Phase 4 | Phase 3 complete | n8n Schedule Trigger, HTTP Request | ✅ Done (Python scheduler) | Artist popularity changes weekly. A new song release can triple an artist's streams in 7 days. This scheduled workflow refreshes all artist scores every Monday automatically. Predictions are never based on stale 3-month-old data — with zero human involvement after initial setup.
18 | Phase 4 | Phase 3 complete | n8n Schedule Trigger, HTTP Request | ✅ Done (Python scheduler) | City income levels shift with inflation, new venues open, populations shift. This workflow refreshes city data monthly so the model uses reasonably current purchasing power figures. Set it once and it runs automatically forever.
19 | Phase 4 | Tasks 18,19 | n8n HTTP Request (FastAPI /recalculate) | ⚠️ Partial | After refreshing raw Spotify and YouTube data, Spearman Correlation and PCA must re-run to update the Artist Power Index. Without this workflow, refreshed raw data would sit in the database while predictions still use the stale old Artist Power scores.
20 | Phase 4 | Phase 3 complete | n8n Webhook, HTTP Request, PostgreSQL | 🔲 Not Started | When a user searches for an artist not yet in your database, instead of showing an error, this workflow auto-fetches their Spotify/YouTube data, generates their Artist Power Index, stores it, and proceeds with the prediction — all invisibly. The product feels complete from day one.
21 | Phase 4 | Phase 3 complete | n8n PostgreSQL Node | 🔲 Not Started | Every prediction is logged: artist, city, all parameters, Ri score, timestamp. This log is your future ML training dataset. The more predictions you accumulate and validate against real outcomes, the more accurate your next-generation machine learning model will be.
22 | Phase 4 | Backend Task 27 | n8n Webhook, PostgreSQL Node | 🔲 Not Started | When a promoter marks 'This show sold out' on the dashboard, this workflow captures that real-world outcome and links it to the original prediction record. This closes the feedback loop — the single most important step toward eventually replacing your formula with a trained AI model.

## Sheet3
🎨 FRONTEND / DASHBOARD TASKS — Concert Success Predictor ¦ Indian Market
Dashboard UI · Artist tab · City tab · Success Predictor tab · UX flows
# | Screen / Component | Depends On | Tech Stack | ✅ Done | 💬 Why This Matters (Plain English)
🏗️ PHASE 1 — Project Setup & Design System
1 | Phase 1 | — | React, Vite, TailwindCSS, shadcn/ui | ✅ Done | This is setting up the blank canvas before painting. React is the framework, Tailwind handles styling, and shadcn gives pre-built professional UI components. Starting with the right tools means your dashboard looks polished from day one without writing custom CSS from scratch.
2 | Phase 1 | Task 1 | Figma, TailwindCSS config | ✅ Done | A design system is the visual rulebook for your entire product. Decide brand colors, font sizes, and button styles once — every screen follows those rules. Without this, each page looks different and the product feels unprofessional. Investors and users notice immediately.
3 | Phase 1 | Task 2 | Figma | ✅ Done | Wireframing is blueprinting before construction. Design every screen in Figma first. Fixing a design in Figma takes 10 minutes. Fixing it in code takes 2 hours. This step alone saves 2–3 weeks of development time and prevents the most expensive kind of rework.
4 | Phase 1 | Task 1 | React Router v6 | 🔲 Not Started | Routing controls which page appears when a user navigates the app. Without proper routing, every click reloads the entire app (jarring and slow). React Router makes navigation feel instant and smooth — essential for a professional dashboard experience.
5 | Phase 1 | Task 1 | Zustand | ✅ Done | Zustand is shared memory for your frontend. When a user selects Arijit Singh on the Artist tab, the Predictor tab needs to know this without the user re-entering it. Without global state, each tab is isolated and users must repeat themselves constantly — extremely frustrating.
6 | Phase 1 | Tasks 1,4 | Axios, React Query | ✅ Done | A clean communication layer between your frontend and n8n. Instead of every component writing its own API call and error handling, all calls go through this service. If the API changes, you fix it in one place instead of hunting through 20 different components.
👤 PHASE 2 — Artists Tab
7 | Phase 2 | Phase 1 complete, n8n Workflow 1 | React, Axios, shadcn Combobox | ✅ Done | The search bar is the most-used element in your app. It should suggest artists after 300ms of typing — not on every keystroke (that would flood your API). Debouncing controls this. Autocomplete makes the app feel fast and intelligent rather than making users type full names perfectly.
8 | Phase 2 | Task 7 | React, TailwindCSS | ⚠️ Partial | After selecting an artist, users see a rich profile confirming they chose the right person — photo, genre, language, combined metrics. This builds trust: users can verify the data before running a prediction and catch any mix-ups (e.g., two artists with similar names).
9 | Phase 2 | Task 8 | Recharts, Framer Motion | ⚠️ Partial | A circular gauge showing Artist Power: 82/100 communicates strength instantly — more powerful than a plain text number. Green = strong, amber = moderate, red = weak. This is the visual centrepiece of the Artist tab and the first thing users emotionally react to.
10 | Phase 2 | Task 9 | Recharts | 🔲 Not Started | Shows users WHY an artist scored what they scored. '70% Spotify-driven, 30% YouTube-driven' tells a Tier-1 city promoter this artist is perfect for their market. '15% Spotify, 85% YouTube' tells a Tier-2 promoter the real fanbase is in smaller cities. Transparency builds product trust and perceived intelligence.
11 | Phase 2 | Task 8 | react-simple-maps, Recharts | ⚠️ Partial | A geographic visualisation showing an artist's top 10 cities by fan density. A Guwahati promoter can instantly see if Arijit Singh's fanbase includes Northeast India or is only concentrated in Mumbai/Delhi. This directly answers the core question: 'Should I book this artist for my city?'
12 | Phase 2 | n8n Weekly Refresh Workflow | React, Recharts | ⚠️ Partial | A weekly-refreshed leaderboard of the hottest artists right now. Users have a reason to come back weekly even without running a prediction — building a habit. Also serves as a discovery tool for promoters open to booking whoever is trending rather than a specific name.
🏙️ PHASE 3 — Cities Tab
13 | Phase 3 | Phase 1 complete, Backend Task 12 | React, react-simple-maps | ⚠️ Partial | An interactive map of India where clicking a state filters to that state's cities. Far more intuitive than a dropdown with 600+ city names. Promoters who think regionally ('I want Northeast India') can explore visually. This immediately signals that your product is premium and thoughtfully designed.
14 | Phase 3 | Task 13 | React, TailwindCSS | ⚠️ Partial | Once a city is selected, display its economic fingerprint. A promoter needs to know at a glance: Can this city afford my tickets? Is the audience young? Do they speak the artist's language? Are there suitable venues? All answered in one card — no separate research needed.
15 | Phase 3 | Task 14 | Recharts RadarChart | 🔲 Not Started | A radar chart showing 5 city dimensions reveals nuance a single score cannot. Guwahati might score low on income but high on youth population and concert enthusiasm. This multi-dimensional view is what separates your product from a simple score calculator — it gives promoters strategic intelligence.
16 | Phase 3 | Backend Task 13 | React, shadcn Table | ✅ Done | Displaying available venues within the city profile saves promoters hours of research and directly feeds into the Predictor tab. When a user selects a venue here, its capacity and type (indoor/outdoor) auto-populate the prediction form — a smooth workflow that feels professionally designed.
17 | Phase 3 | Backend Task 27 | React, shadcn Timeline | ⚠️ Partial | As promoters log real concert outcomes, this timeline shows the history of concerts in a city. 'March 2024: Artist X, 8000 capacity, Sold Out.' This social proof helps a new promoter understand a city's concert culture and appetite before committing to a booking — invaluable for Tier-2 cities with little public data.
🎯 PHASE 4 — Success Predictor Tab (Core Product)
18 | Phase 4 | Phases 2+3 complete | React, shadcn Form, date-fns | ✅ Done | This is the main control panel. Every field matters: artist, city, indoor/outdoor (weather penalty), venue capacity (can the artist fill it?), ticket price (economic friction), and date (weather season + competing events). Each field feeds a specific mathematical factor in your model.
19 | Phase 4 | Task 18 | React, Framer Motion | ⚠️ Partial | Your prediction takes 3–5 seconds. A blank screen for 5 seconds feels broken. A step-by-step progress animation transforms the wait into an experience. Users feel the system is working hard for them. This single UX detail dramatically improves perceived product quality.
20 | Phase 4 | Task 18 | React, Recharts, Framer Motion | ⚠️ Partial | This is the money shot — what users have been waiting for. Show the success probability as a large bold percentage, a colour-coded tier badge, and a recommended venue size. Make it visually dramatic. This screen is what users screenshot and share. It IS your product.
21 | Phase 4 | Task 20 | Recharts, React | ⚠️ Partial | Showing only the final score is a black box. Showing what drove it is trusted intelligence. 'Artist Power: Strong ✅ ¦ City Purchasing Power: Medium ⚠️ ¦ Ticket Price Friction: High ❌'. A promoter can now act on this — lower the ticket price to reduce friction and improve their score. Actionable = valuable.
22 | Phase 4 | Task 21 | React, Recharts | 🔲 Not Started | This transforms your tool from a calculator into a strategy advisor. Drag the ticket price slider from ₹2000 to ₹1500 and watch the success score jump from 68% to 79% in real time. This interactivity is worth 10x the subscription price to a professional promoter making a booking decision.
23 | Phase 4 | Backend Task 26 | React, shadcn Table, React Query | ✅ Done | Power users — agencies booking multiple shows per month — need to look back at past predictions. This page shows everything they have run, filterable by city or artist. It also lets them mark outcomes ('This one sold out'), feeding your training data pipeline. Core retention feature for professional subscribers.
24 | Phase 4 | Task 22, n8n Feedback Workflow | React, shadcn Modal | 🔲 Not Started | After a concert, a promoter returns to their prediction history and submits the outcome. This single feature converts your mathematical model into a self-improving system. Every submitted outcome is labelled training data. The more outcomes collected, the smarter your next model generation becomes.
🔐 PHASE 5 — Auth, Onboarding & Polish
25 | Phase 5 | Phase 4 complete | React, Clerk / Supabase Auth | ⚠️ Partial | Users need accounts to save prediction history and access personalised features. Google OAuth reduces signup friction dramatically — most users abandon a product if registration requires filling out a long form. One click with Google and they are in. Proven to increase conversion rates by 30–50%.
26 | Phase 5 | Task 25 | React, react-joyride | 🔲 Not Started | A new user landing on your dashboard for the first time is completely lost. A guided 3-step walkthrough teaches the workflow in 90 seconds without a manual or support call. Products with good onboarding retain 40–60% more users in the first week. Do not skip this.
27 | Phase 5 | Phase 4 complete | TailwindCSS responsive classes | 🔲 Not Started | Indian concert promoters are often on their phones. If your dashboard only works on desktop, you lose a massive share of your target market. TailwindCSS makes responsive design straightforward — each component needs mobile breakpoints. This is non-optional for the Indian market.
28 | Phase 5 | Phase 4 complete | React.lazy, React Query, Vite | 🔲 Not Started | Slow apps lose users — especially in Tier-2 cities with variable internet. Lazy loading means only the current tab's code loads initially (faster first load). React Query caches API results so switching tabs does not re-fetch data. These optimisations separate a polished product from an amateur one.
29 | Phase 5 | Phase 5 tasks complete | Playwright / Cypress | 🔲 Not Started | Automated tests simulate a real user clicking through your entire app. Run these every time you push new code. This catches bugs before paying customers do and prevents the nightmare of a broken prediction engine going unnoticed for days while users churn.
30 | Phase 5 | Task 29 | Vercel, GitHub Actions | 🔲 Not Started | Vercel deploys your React app globally in minutes. Connect to GitHub and every code push to main auto-deploys — no manual steps. Your app gets a real URL, a fast global CDN, and HTTPS automatically. This is the moment your product becomes real, shareable, and ready to demo to investors.